Weekly Progress Report – 2nd Feb 2025

Project Name: World Bank Project 4 - P179939
Team Members: Kumar Saurav Jha, Abishek Chiffon Muthuraja, Swathi Kannetti Ramana Reddy
Trello board URL: https://trello.com/invite/b/6788251adfe2bea47ec8b9ac/ATTI8bf2432c6d87d6e9ff473f496725a3055758E8DD/dats650113-wb-project-4

Summary: Summary: The team has been actively working on understanding the dataset shared by the World Bank project members. The documentation review provided insights into transport expenditure, last mode of transport (lastMOT), and CIF values. The recent meeting with the World Bank team (Jan 29, 2025) highlighted data gaps, potential solutions for missing values, and the importance of integrating Africa-specific data into freight flow models. The focus now is on acquiring the full dataset, setting up the data pipeline, and preparing for in-depth exploratory data analysis (EDA) ahead of the next meeting in two weeks.

Overall Progress: On Track

Tasks Completed This Week:

- Going through the dataset

  - Understood the different fields of the dataset and how they’re calculated, such as transport expenditure and lastMOT (last mode of transport).

- Forming deeper insights about the problem statement

  - How it’s impacting the issue of food insecurity and exploitation of natural minerals.

- World Bank Meeting (Jan 29, 2025):

- Discussed data gaps and potential solutions such as the mirroring method for estimating missing transport cost values.

- Talked about enriching global freight flow models with Africa-specific data.

- Highlighted supply chain inefficiencies, particularly high intra-Africa transport costs.

- Explored how AI tools can help identify missing data and enhance decision-making.

- Discussed the importance of collaborating with past teams that worked on similar projects to gain insights.

- Considered integrating CIF values and weight-based conversions to ensure accurate transport cost estimates.

- Emphasized the need for a structured data pipeline to facilitate easier analysis and scalability.

Challenges Encountered:

N/A

Next Week's Goals:

- Request access to the actual dataset from the World Bank team.

- Follow up on the GitHub repository decision—clarify whether to create a new one or use an existing one.

- Seek access to the research code used in the European transport model from the referenced research paper.

- Continue exploratory data analysis (EDA) and prepare findings for the next meeting after receiving the dataset

- Begin defining key metrics for evaluating transport mode efficiency within Africa.

- Outline potential use cases for AI models to predict transport cost trends and optimize decision-making.

Progress on Deliverables:

N/A

Timeline Review:

- Deadline for data processing and analysis is set for February 13, 2025, to present findings in the next meeting.

- No other changes as of now, too early to comment.

Resources and Support Needed:

N/A

Additional Notes:

N/A